## Project Mandate
Project Mandate
Delivering a centralized School Management System that enables administrators, teachers, finance staff and parents to efficiently manage core academic and administrative processes through a single digital platform.
The aim is to replace manual, paper-based processes for student registration, attendance tracking, fee management, result processing, and parent communication with an integrated solution that improves data accuracy, provides real-time visibility into school operations, and enhances decision-making, stakeholder satisfaction, and overall operational efficiency.

## Summary of Epics and Features
SUMMARY OF FEATURES AND EPICS
Epic ID | Epic Name | Feature ID | Feature Name
EP001 | Student Registration Management | F001 | Student Registration
|  | F002 | Class Assignment
EP002 | Attendance Management | F003 | Daily Attendance Recording
|  | F004 | Duplicate Attendance Prevention
|  | F005 | Parent Absence Notification
EP003 | Fee Management | F006 | Payment Recording
|  | F007 | Payment Verification
|  | F008 | Receipt Generation
|  | F009 | Outstanding Balance Tracking
EP004 | Result Management | F010 | Score Entry
|  | F011 | Automatic Grade Calculation
|  | F012 | Result Approval
|  | F013 | Result Publication
EP005 | Communication Management | F014 | Automated Notifications
EP006 | Reporting and Dashboard | F015 | Operational Dashboard
EP007 | Security and Access Control | F016 | Role-Based Access Control
Project Mandate
Delivering a centralized School Management System that enables administrators, teachers, finance staff and parents to efficiently manage core academic and administrative processes through a single digital platform.
The aim is to replace manual, paper-based processes for student registration, attendance tracking, fee management, result processing, and parent communication with an integrated solution that improves data accuracy, provides real-time visibility into school operations, and enhances decision-making, stakeholder satisfaction, and overall operational efficiency.

## Epics & Features Documentation
EPICS LIST AND FEATURES LIST DOCUMENTATION
EPIC ID | EPIC NAME | FEATURE ID | FEATURE NAME | USER STORY ID | USER STORY | ACCEPTANCE CRITERIA (GHERKIN FORMAT) | PRIORITY USE MOSCOW OR L/M/H | STATUS
EP-001 | Student Registration Management | FE-001 | Student Registration | US-001 | As an Admin, I want to register a new student so that the student can be enrolled and assigned to a class. | Given the Admin is on the Student Registration page When all mandatory student and parent details are entered and submitted Then the system shall validate the data, generate a unique student ID, and save the student record successfully. | Must Have | To Do
EP-001 | Student Registration Management | FE-002 | Class Assignment | US-002 | As an Admin, I want to assign a registered student to a class so that the student can participate in academic activities. | Given an active student record exists When the Admin selects an academic session and class and saves the assignment Then the system shall assign the student to the selected class successfully. | Must Have | To Do
EP-002 | Attendance Management | FE-003 | Daily Attendance Recording | US-003 | As a Teacher, I want to mark attendance electronically so that student attendance is recorded accurately | Given the Teacher selects a class and date When the Teacher marks all students and clicks Submit Then the system shall save the attendance and display a confirmation message | Must Have | To Do
EP-002 | Attendance Management | FE-004 | Duplicate Attendance Prevention | US-004 | As a Teacher, I want the system to prevent duplicate attendance submissions so that records remain accurate. | Given attendance has already been submitted for the selected class and date When the Teacher attempts to submit attendance again Then the system shall display a warning message and prevent duplicate submission. | Must Have | To Do
EP-002 | Attendance Management | FE-005 | Parent Absence Notification | US-005 | As a Parent, I want to receive a notification when my child is marked absent so that I am informed immediately | Given a student is marked Absent When the Teacher submits attendance Then the system shall send an SMS or email notification to the parent. | Should Have | To Do
EP-003 | Fee Management | FE-006 | Payment Recording | US-006 | As a Finance Officer, I want to record fee payments so that student accounts are updated accurately | Given the Finance Officer selects a student account When a payment amount and payment method are entered and submitted Then the system shall record the payment and update the student payment status. | Must Have | To Do
EP-003 | Fee Management | FE-007 | Payment Verification | US-007 | As a Finance Officer, I want to verify bank transfers before posting payments so that only confirmed payments are recorded. | Given a bank transfer payment is awaiting confirmation When the Finance Officer checks the payment status Then the system shall allow posting only if the payment is confirmed; otherwise, the payment remains pending. | Must Have | To Do
EP-003 | Fee Management | FE-008 | Receipt Generation | US-008 | As a Parent, I want to receive a payment receipt so that I have proof of payment. | Given a payment has been recorded successfully When the transaction is completed Then the system shall generate a receipt with a unique receipt number and make it available for printing or email. | Must Have | To Do
EP-003 | Fee Management | FE-009 | Outstanding Fees Tracking | US-009 | As a Parent, I want to view outstanding fees to pay before the beginning of each term so that I plan accordingly | Given the Parent is logged into the portal When the Parent views the fee statement Then the system shall display total fees to be made for the term | Should Have | To Do
EP-004 | Result Management | FE-010 | Score Entry | US-010 | As a Teacher, I want to enter assessment and exam scores so that student performance can be calculated. | Given the Teacher selects a class and subject When valid scores are entered and saved Then the system shall store the scores successfully. | Must Have | To Do
EP-004 | Result Management | FE-011 | Automatic Grade Calculation | US-011 | As a Teacher, I want the system to calculate totals, averages, and grades automatically so that errors are reduced. | Given student scores have been entered When the Teacher saves the scores Then the system shall calculate totals, averages, and grades automatically. | Must Have | To Do
EP-004 | Result Management | FE-012 | Result Approval | US-012 | As an Admin, I want to review and approve results before publication so that only validated results are released. | Given results have been submitted by the Teacher When the Admin approves the results Then the system shall mark the results as Approved and make them available for publication. | Must Have | To Do
EP-004 | Result Management | FE-013 | Result Publication | US-013 | As a Parent, I want to access my child’s results online so that I can monitor academic performance | Given results are approved When the Parent views the result portal Then the system shall display the student’s published results. | Should Have | To Do
EP-005 | Communication Management | FE-014 | Automated Notifications | US-014 | As an Admin, I want to send automated notifications to parents so that they receive timely updates. | Given a trigger event occurs (attendance, fee, or result update) When the system processes the event Then the system shall send the relevant notification to the parent. | Should Have | To Do
EP-006 | Reporting and Dashboard | FE-015 | Operational Dashboard | US-015 | As an Admin, I want to view dashboards for attendance, fees, and results so that I can monitor school performance in real time. | Given the Admin opens the dashboard When dashboard data is loaded Then the system shall display key metrics for attendance, fees, and results. | Could Have | To Do
EP-007 | Security and Access Control | FE-016 | Role-Based Access Control | US-016 | As a System Administrator, I want to assign user roles and permissions so that users access only authorized functions. | Given user roles are configured When a user logs into the system Then the system shall grant access only to features permitted for that user’s role. | Must Have | To Do

## Product Backlog - User Story
|  |  |  | PRODUCT BACKLOG/USER STORY TEMPLATE |  |  | This is a sample - Edit to align with your project mandate.
EPIC ID | EPIC NAME OR TITLE | FEATURE ID | FEATURE | USER STORY ID | USER STORY priority either using MOSCOW or RANKING (high, medium, low) | AS A <type of user> I WANT TO <perform some task> SO THAT I CAN <achieve some goal> | ACCEPTANCE CRITERIA <GERKIN SYNTAX> | FINAL STORY ? (MEETING THE DEFINITION OF READY?) | SPRINT ?
EP-001 | Access managemnt | FR-001 | Register | US-001 | High | AS A New user I WANT to register by creating a username and password SO THAT I CAN the system can remember my information. | GIVEN that I am a new user, WHEN I go to the registration page , enter my information and complete registration. THEN I am successfully registered and will be able to log in with my chosen credentials GIVEN that I am a new user, WHEN I go to register my details and enter my information and get the error 'password not strong enough, try again' THEN I can try using a stronger and more secure password. |  | SPRINT 1
EP-001 | Access managemnt | FR-002 | Secure Log in | US-002 | High | AS A registered user. I WANT to log in with my username and password SO THAT the system can authenticte me and I can be confident my details are secure. | GIVEN that I am a registered user, WHEN I go to the log in page and enter my username and password and click on Log in with my registered details, THEN I should be able to log into the platform for the first time. GIVEN that I am a registered user and logged out, WHEN I go to the log in page and enter my username with an incorrect password and cannot log on. THEN I should be able to click 'forgot password' and get an authentication code sent to my phone to change my password. |  | SPRINT 1
EP-001 | Access managemnt | FR-003 | Verification | US-003 | High | AS A user I WANT to receive a verification code SO THAT I can be sure my log in details are protected from password leaks and unauthorized access. | GIVEN that I am a user, WHEN I have entered my log in details THEN I should be able to recieve a verification code via the method I selected at registration either by sms or email. GIVEN that I am a user and I go to log in WHEN I dont receieve a verification code via email or sms THEN then I will select, 'resend code' and wait for another verification code to be sent. |  | SPRINT 2
EP-001 | Access managemnt | FR-004 | Create Profile | US-004 | High | AS A user I WANT to be able to create a profile SO THAT I have all my contact and apartment details in one place. | GIVEN that I am a user, WHEN I go to create profile THEN I should be able to add my profile photo, name, personal information, contact details, flat number and save to my profile. GIVEN that I am a user and I am creating my profile WHEN I leave required fields blank THEN the system should highlights the empty fields And displays an error message specifying the missing information so that I can enter them.
EP-002 | Navigation dashboard | FR-005 | Create maintenance request | US-005 | High | As a user, I want a dashboard that provides an overview of my activities and performance metrics, so that I can easily track my requests, view recent actions, and identify any areas that needs attention. | GIVEN that I am on the dashboard, WHEN I click maintanace request. THEN I am directed to the maintanance page. GIVEN that I click 'maintance request' on the dashboard WHEN I see the maintanance page is not loading, THEN I go back to the dashboard to click maintanance request again.
EP-002 | Navigation dashboard | FR-006 | Request Booking | US-006 | High | AS A user I WANT TO request a booking SO THAT I can reserve a parking space for my guest. | GIVEN that I am on the dashboard, WHEN I click request booking, THEN I am redirected to the booking page. GIVEN WHEN THEN
EP-003 | Navigation dashboard | FR-007 | Access Payment portal | US-007 |  | AS A user I WANT TO make a payment SO THAT I can complete and confirm payment for new keys. | GIVEN WHEN THEN GIVEN WHEN THEN
EP-003 | Navigation dashboard | FR-008 | Terms, condition and privacy agreements | US-008 |  | AS A user I WANT TO read the terms, conditions and privacy policy SO THAT I am confident that Renzo property management will keep my information safe | GIVEN WHEN THEN GIVEN WHEN THEN
EP-003 | Navigation dashboard | FR-009 | Updates and notification | US-009 |  | AS A user I WANT TO check my updates and notifications SO THAT I am aware of new property changes, property activity and progress of my requests, | GIVEN WHEN THEN GIVEN WHEN THEN
EP-004 | Communication | FR-010 | Send messages | US-010 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-005 | Communication | FR-011 | Live chat | US-011 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-006 | Communication | FR-012 | Message history | US-012 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-007 | Booking | FR-013 | View availability | US-013 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-008 | Booking | FR-014 | Reserve and book amenities | US-014 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-009 | Booking | FR-015 | Manage existing reservation | US-015 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-010 | Booking | FR-016 | Rules and guidelines for booking. | US-016 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-011 | Maintanance request | FR-017 | Submit request | US-017 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-012 | Maintanance request | FR-018 | View and manage requests | US-018 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-013 | Maintanance request | FR-019 | track status updates | US-019 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-014 | Maintanance request | FR-020 | Announcement feeds | US-020 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-015 | updates and Notifications | FR-021 | Notifications | US-021 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-016 | updates and Notifications | FR-022 | Notifications preferences/ settings | US-022 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-017 | Payment | FR-023 | Secured payment processing | US-023 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-018 | Payment | FR-024 | Payment history and reciepts | US-024 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN
EP-019 | Payment | FR-025 | Set up recurring payment and reminder. | US-025 |  | AS A user I WANT TO SO THAT I | GIVEN WHEN THEN GIVEN WHEN THEN