## Sheet1
Requirements Traceability Matrix (RTM)
School Management System Project
The Requirements Traceability Matrix (RTM) links business objectives and identified gaps to functional requirements, user stories, test scenarios, and success metrics. It demonstrates end-to-end traceability and shows that every requirement supports a business need. The Requirements Traceability Matrix ensures that every requirement in the School Management System is directly linked to a business objective, validated through testing, and measured against defined success criteria
RTM ID | Business Objective | Gap Description | Requirement ID | Functional Requirement | Epic / Feature | User Story ID | Priority (MoSCoW) | Test Case ID | KPI / Success Metric | Status
RTM-001 | Digitize student registration | Student records are maintained manually, causing duplicate and incomplete records | FR-001 | The system shall allow Admin to register a new student and generate a unique student ID | Student Registration Management /Student Registration | US-001 | Must Have | TS-001 | Reduce registration time by 60% | To Do
RTM-002 | Assign students to classes | Class assignments are tracked manually and are difficult to update | FR-002 | The system shall allow Admin to assign a registered student to a class for an academic session | Student Registration / Class Assignment | US-002 | Must Have | TS-002 | 100% of students assigned to classes electronically | To Do
RTM-003 | Digitize attendance tracking | Attendance is recorded in paper registers and reports are delayed | FR-003 | The system shall allow Teachers to record daily attendance by class and date | Attendance Management/ Daily Attendance Recording | US-003 | Must Have | TS-003 | Reduce attendance recording time by 50% | To Do
RTM-004 | Prevent duplicate attendance | Teachers may submit attendance more than once for the same class and date | FR-004 | The system shall prevent duplicate attendance submissions | Attendance Management / Duplicate Attendance Prevention | US-004 | Must Have | TS-004 | 0 duplicate attendance records | To Do
RTM-005 | Notify parents of absences | Parents are informed late when students are absent | FR-005 | The system shall send absence notifications to parents | Attendance Management / Parent Absence Notification | US-005 | Should Have | TS-005 | 95% notification delivery rate | To Do
RTM-006 | Record fee payments electronically | Payments are recorded manually, leading to reconciliation issues | FR-006 | The system shall allow Finance Officers to record student fee payments | Fee Management / Payment Recording | US-006 | Must Have | TS-006 | Reduce payment posting time by 50% | To Do
RTM-007 | Verify bank transfers | Unverified transfers may be posted incorrectly | FR-007 | The system shall require verification before posting bank transfer payments | Fee Management / Payment Verification | US-007 | Must Have | TS-007 | 100% of transfers verified before posting | To Do
RTM-008 | Generate payment receipts | Receipts are written manually and can be lost | FR-008 | The system shall automatically generate a receipt after successful payment | Fee Management / Receipt Generation | US-008 | Must Have | TS-008 | 100% of payments produce receipts | To Do
RTM-009 | Show outstanding balances | Parents have limited visibility into unpaid fees | FR-009 | The system shall display fee statements and outstanding balances | Fee Management / View Outstanding Balance | US-009 | Should Have | TS-009 | Reduce balance enquiries by 40% | To Do
RTM-010 | Capture student scores | Scores are entered in spreadsheets and are prone to errors | FR-010 | The system shall allow Teachers to enter assessment and exam scores | Result Management / Enter Scores | US-010 | Must Have | TS-010 | Reduce score entry errors by 80% | To Do
RTM-011 | Automate grade calculations | Totals and grades are calculated manually | FR-011 | The system shall calculate totals, averages, and grades automatically | Result Management / Calculate Grades | US-011 | Must Have | TS-011 | 100% automated grade calculation | To Do
RTM-012 | Approve results before release | Results may be published without management review | FR-012 | The system shall require Admin approval before publication | Result Management / Approve Results | US-012 | Must Have | TS-012 | 100% of results approved before publication | To Do
RTM-013 | Publish results online | Parents wait to collect printed report cards | FR-013 | The system shall allow parents to view approved results online | Result Management / View Results | US-013 | Should Have | TS-013 | 90% of results accessed online | To Do
RTM-014 | Automate communications | Notifications are sent manually or inconsistently | FR-014 | The system shall send automated notifications for attendance, fees, and results | Communication / Send Notification | US-014 | Should Have | TS-014 | 95% successful message delivery | To Do
RTM-015 | Provide operational dashboards | Management lacks real-time visibility into key metrics | FR-015 | The system shall provide dashboards for attendance, fees, and academic performance | Reporting / View Dashboard | US-015 | Could Have | TS-015 | Reports available in under 5 seconds | To Do
RTM-016 | Enforce access control | Sensitive information is accessible without formal controls | FR-016 | The system shall enforce role-based access control | Security / Role-Based Access Control | US-016 | Must Have | TS-016 | 100% compliance with access rules | To Do
Portfolio Note
Recommended File Format
Maintain the RTM in Excel for easy filtering and sorting. Include tabs for:
Requirements Traceability Matrix
Test Scenarios
KPI Definitions
Suggested Filters for Interview Demonstrations
Use Excel filters to quickly show:
Must Have requirements
All requirements for a specific Epic
Requirements linked to a particular KPI
Requirements that are To Do / In Progress / Done